Ru9 Internal Wiki AI Bot

Phase 1 Proposal — For Owner Review

Date: 22 April 2026

Prepared for: Ru9 Owner

Prepared by: Ru9 AI / Engineering Team

# 1. Executive Summary

This proposal requests approval to build Phase 1 of Ru9's Internal Wiki AI Bot — a Lark-native assistant that answers any Ru9 employee's question by drawing on content already stored in Ru9's Lark Suite, with clear source citations back to the original document.

Phase 1 is deliberately scoped to question-answering only: no document editing, no automated actions, no database queries. This keeps risk low, compresses time to first value to roughly 10 weeks, and establishes the technical foundation for Phase 2 (Ads Intelligence skill) and later capabilities.

Estimated Phase 1 investment: approximately US$2,800 in one-time hardware, ~$70 in account setup, and ~$650–$1,400 per month in recurring software and cloud costs. Total Phase 1 spend over 10 weeks plus a 3-month operating window is estimated at US$5,400–$8,500.

We need the owner's approval on (1) overall budget, (2) Lark admin access for the bot app, (3) assignment of an IT/security sponsor, and (4) engineering team allocation.

# 2. Phase 1 Objectives

- Every Ru9 employee, in every department, can ask a plain-language question in Lark and receive an accurate, cited answer drawn from Ru9's existing Lark Docs, Wiki, and Base content.

- Answers respect each employee's existing Lark document permissions — no content leaks across departments.

- Secondary chat surfaces on Telegram and Zalo, for employees who prefer those channels or are off-Lark (e.g., field staff).

- Measurable quality targets: ≥70% answer accuracy on a weekly QA sample, median response time under 15 seconds, and ≥60% of Ru9 staff using the bot at least once per week by end of month 2.

- Zero permission-leak incidents — validated via red-team testing before launch.

# 3. Scope — What Phase 1 Will (and Will Not) Do

## In scope

- Ingest content from Lark Docs, Lark Wiki, and Lark Base (tables).

- Respect Lark document permissions at the moment of every answer.

- Chat surface on Lark (primary), Telegram, and Zalo (secondary, same backend).

- Every answer includes citations linking to the source Lark document with a "last updated" timestamp.

- Feedback loop (thumbs up/down) and weekly quality review.

- A 100-question evaluation set covering every department, used to measure accuracy before launch and weekly thereafter.

## Out of scope for Phase 1

- Creating, editing, or posting documents back to Lark.

- Taking actions — no ticket creation, message-sending, or workflow triggers.

- Answering questions against databases, BI tools, or live data warehouses.

- Voice interface.

- The Ads Intelligence skill (Phase 2).

# 4. Technical Approach — Claude + RAG on Lark

The bot is built on Claude (Anthropic's frontier language model) combined with a Retrieval-Augmented Generation (RAG) pipeline — referred to as the "OpenClaw" stack in our internal planning. This is a proven, open architecture that combines Claude's reasoning with Ru9-specific knowledge retrieved in real time from Lark.

## How it works

1. Lark connectors pull content from Docs, Wiki, and Base via the Lark Open Platform APIs. Change webhooks keep the index fresh within minutes of any edit.

2. Content is split into chunks, converted to embeddings by a multilingual model that handles Vietnamese and English, and stored in a vector database alongside each source document's Lark access control list (ACL).

3. When an employee asks a question, the bot performs hybrid search (keyword + semantic), filters results against that employee's Lark permissions, and reranks the top matches. Claude then composes a cited answer from the top results — or responds "I don't know" if retrieval is weak.

4. The Lark bot, Telegram bot, and Zalo Official Account share the same backend service. Employees link their identities once so permissions carry across all three surfaces.

## Why this architecture

- Full control over Lark permission enforcement — off-the-shelf products (Glean, Guru, etc.) do not integrate cleanly with Lark or Zalo.

- No vendor lock-in on the knowledge layer; Ru9 owns the index and can extend it in Phase 2.

- Bilingual support (Vietnamese + English) from day one, through the choice of multilingual embedding model.

- Same foundation powers Phase 2's Ads Intelligence skill; that effort will add data sources (ad platforms) and new tools to the same agent, not build a second system.

# 5. Equipment & Procurement

The procurement list below covers everything needed to stand up Phase 1. Costs are estimates at April 2026 prices and will be refined once vendors are selected.

## 5.1 Software & Services (recurring)

| Item | Purpose | Est. Cost (USD) | Type |
| --- | --- | --- | --- |
| Anthropic Claude API | Core LLM powering bot answers (Sonnet primary, Opus fallback) | $400–$800 / mo | Recurring |
| Claude Code (Team) | Engineering productivity — developers use Claude Code to build & maintain the system. 3 seats. | $60–$300 / mo | Recurring |
| Vector database (Supabase / pgvector or Qdrant Cloud) | Stores document embeddings + Lark ACLs; powers retrieval. | $25–$150 / mo | Recurring |
| Cloud hosting (AWS / GCP) — backend + worker | Runs bot backend, ingestion workers, chat adapters. | $80–$200 / mo | Recurring |
| Multilingual embedding model (Cohere multilingual or BGE-M3 self-hosted) | Converts Vietnamese + English text into vectors. | $30–$100 / mo | Recurring |
| Monitoring (Sentry / Better Stack) | Error tracking, uptime monitoring, alerting. | $30–$80 / mo | Recurring |
| Domain + SSL certificate | bot.ru9.com (or equivalent) for webhooks and admin UI. | ~$20 / year | Recurring |
| CI / source hosting (GitHub Team) | Code, review, deployment pipeline. | $16 / user / mo | Recurring |

## 5.2 Hardware (one-time)

The Mac minis serve as developer workstations for the engineering team plus a dedicated build/staging machine. Apple silicon is chosen for energy efficiency, quiet operation, and strong local-inference performance — useful for testing embeddings and reranking before shipping to production.

| Item | Purpose | Est. Cost (USD) | Type |
| --- | --- | --- | --- |
| Mac mini M4 (base, 16GB / 256GB) × 2 | Developer workstations for the 2 engineers building the bot. | $1,200 | One-time |
| Mac mini M4 Pro (24GB / 512GB) × 1 | Shared build / staging / small on-prem inference server. | $1,600 | One-time |
| External monitors + peripherals (optional) | Second monitor, keyboard, mouse per dev — skip if devs already equipped. | $500 (optional) | One-time |
| UPS + network upgrade (optional) | Uninterrupted power for staging Mac mini; gigabit switch if needed. | $200 (optional) | One-time |

## 5.3 Accounts & Integrations

| Account / Integration | Purpose | Est. Cost (USD) |
| --- | --- | --- |
| Lark Open Platform — internal app registration | Scopes: Docs read, Wiki read, Base read, Bot messaging, User info. | Free (Lark admin approval) |
| Telegram Bot API | Bot token via @BotFather. | Free |
| Zalo Official Account (OA) | Verified OA for business messaging; verification fee may apply. | ~$50 (one-time) |
| Anthropic API org account | Organization-level account with usage caps and billing. | Free to open |
| Cloud account (AWS or GCP) | Organization-level account for hosting. | Free to open |

# 6. Timeline

Phase 1 is scoped to a 10-week delivery window. The critical gate is end of week 5: if retrieval is not hitting ≥70% on the evaluation set, we fix that before moving to the chat surface.

| Phase | Focus |
| --- | --- |
| Weeks 1–2 | Foundations: register Lark app, secure IT approvals, stand up vector DB and embedding model, build a 100-question evaluation set from every department (HR, Eng, Sales, Ops, Finance). |
| Weeks 3–5 | Ingestion + retrieval: build Lark Docs / Wiki / Base connectors with ACL metadata, chunking + embedding pipeline, hybrid retrieval + reranking. Tune until ≥70% accuracy on eval set. |
| Weeks 6–7 | Lark bot: bot authentication, per-user permission enforcement, citation rendering as clickable Lark links, rate limits, logging. Open to engineering only. |
| Weeks 8–9 | Internal beta: 2–3 pilot departments use the bot daily. Daily quality review, fix top 10 recurring issues, tune retrieval. |
| Week 10 | Ru9-wide launch: department-by-department rollout with kickoff messages, office hours, feedback channel. Ship Telegram + Zalo adapters if bandwidth allows (otherwise week 12). |

# 7. Budget Summary

All figures are estimates in US dollars. VND equivalents will be provided once final vendor quotes are received.

| Category | Estimate |
| --- | --- |
| One-time hardware (2× Mac mini M4 + 1× Mac mini M4 Pro) | ~$2,800 USD |
| One-time hardware (optional peripherals + UPS) | ~$700 USD |
| One-time account setup (Zalo OA, domain) | ~$70 USD |
| Recurring — first month (with setup spike) | ~$900–$1,600 USD |
| Recurring — steady state (month 2+) | ~$650–$1,400 USD / mo |
| Phase 1 total (10 weeks, hardware + 3 months recurring) | ~$5,400–$8,500 USD |

Recurring costs scale with usage. The estimates above assume roughly 100–200 active users sending 5–10 messages per day each. Heavier usage increases the Claude API line proportionally; all other lines are largely fixed.

# 8. Team

- 1 × Backend / RAG Engineer (lead) — owns the ingestion pipeline, retrieval, and Claude integration.

- 1 × Integrations Engineer — builds the Lark bot, Telegram and Zalo adapters, and the permissions layer.

- 1 × Part-time PM / Evaluator — maintains the evaluation set, runs weekly QA, coordinates department rollouts.

- 1 × IT / Security Sponsor (from Ru9) — approves Lark app scopes, reviews permission model, signs off before launch.

# 9. Risks & Mitigations

## Permission leakage (highest risk)

If ACLs are not enforced at retrieval time, the bot could surface Finance documents to a Sales team member. Mitigation: store the Lark ACL on every chunk at index time, filter at every query, and red-team test with 20+ cross-department prompts before launch. IT/security sponsor signs off.

## Stale content eroding trust

Employees will stop trusting the bot if it cites outdated documents. Mitigation: webhook-driven incremental sync keeps the index current within minutes of edits; every citation shows the source document's "last updated" date.

## Bilingual content (Vietnamese + English)

Single-language embedding models fail on mixed-language corpora. Mitigation: multilingual embedding model from day one; bilingual queries explicitly included in the evaluation set.

## Adoption

Bots die without usage. Mitigation: seed the launch with 3–5 high-value scripted use cases per department (HR policy lookup, engineering runbooks, finance close calendar, onboarding FAQ) so the first experience is a clear win.

# 10. What We Need From You

To begin week 1 on schedule, we need the following decisions and approvals from the Ru9 owner:

- Budget approval for the estimated Phase 1 spend (hardware + 3 months recurring).

- Lark admin access so the engineering team can register the bot application and approve the required read scopes.

- IT / security sponsor assignment — a named individual from Ru9 who will review the permission model and sign off before Ru9-wide launch.

- Engineering team allocation — either backfill or reallocation of 2 engineers + a part-time PM for 10 weeks.

- Kick-off meeting with department heads to gather evaluation-set questions and identify pilot teams.

Appendix A — Phase 2 Preview (Ads Intelligence Skill)

Once Phase 1 is live, the Ads Intelligence skill becomes a new capability the same agent can call. It will add data sources — Meta Ads, Google Ads, TikTok Ads — and new analysis and generation prompts (campaign performance summaries, creative suggestions, budget reallocation recommendations). The retrieval pipeline, permissions model, chat surfaces, and evaluation framework built in Phase 1 are all reusable. Phase 2 is a capability expansion, not a second product, which is why we are investing in the foundation now.